## 1. Risk Register Template
(ORGANIZATION NAME)
This risk assessment is connected to/aligns with: |  |  | <name of organization or enterprise/branch-wide strategic or operational risk register>
Objective: |  |  | <What is the subject of the risk assessment e.g., Mandate letter, policy, project name, initiative>
Date of the risk assessment: |  |  | <date>
Risk should be reassessed periodically throughout the life of the program or project.
Future date(s) to reassess the risks within the register: |  |  | <date>
Check out the B.C. Enterprise Risk Categories Tool to explore other risks that may affect objectives. | [19 empty] | RISK REPORTING (Optional - Hide/Delete if not in use)
RISK MANAGEMENT PROCESS (For Guidance, See Tab 2) |  | CONTEXT (For Guidance, See Tab 3) | RISK IDENTIFICATION |  |  |  | ANALYSIS Residual risk rating with treatments in place (For Guidance, See Tab 4) |  |  |  | EVALUATION (For Guidance, See Tab 5) |  |  | TREATMENT MANAGEMENT | [5 empty] | TRACKING |  |  |  | RESIDUAL RISK RATING (Risk rating expected / predicted once all treatments, including additional treatments, are in place.) |  |  |  | CURRENT RISK RATING (Current level of risk in light of treatments implemented at this report period.) |  |  |  | RISK TOLERANCE RATING (Risk tolerance executive is willing to accept. This should be provided by executive after having been briefed on the risk, existing and planned treatments, and associated costs.)
RISK # | CATEGORY | BUSINESS OBJECTIVE/ PRIORITY | RISK EVENT | RISK CAUSE | IMPACT | CURRENT TREATMENTS | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | ADEQUACY OF CURRENT TREATMENTS | ACTION | TREND | ADDITIONAL PLANNED TREATMENT | DELIVERABLES | TASK OWNER | DUE DATE | DEPENDENCIES/ INTER-RELATIONSHIPS | STATUS | PROGRESS % | COMMENTS/ ISSUES | FURTHER ACTION | COMPLETION DATE | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP
Add identifiers to better organize and track risks. | Which category does this Risk Event fall under? | What business objective/priority does this Risk Event affect (e.g., Mandate letter, strategic directive, etc.)? | What events could impact the achievement of objectives (can be positive or negative)? | What Risk Cause (trigger, circumstance, uncertainty) could increase the Likelihood of the Risk Event occurring? There are usually multiple Risk Causes leading to a Risk Event. | How would the Risk Event impact the achievement of the objective/priority? | What Treatments are currently in place to manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | How likely? | How severe? | (LxC) | Rating with current treatments in place | Non-existent Inadequate Adequate Robust | Will you do more to manage the risk (treat) or choose to accept and monitor? | If applicable, has this risk rating changed over time? Has column J increased (upward trend), decreased (downward trend) or not changed (static) | What Treatments are needed to further manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | Future Treatments will come in what form (e.g., a project plan, a briefing note, report, funding request, other)? | Who will take the lead on this mitigation? | When should the deliverable be ready? (Optional) | Do the Risk Event or Treatments depend on another team or organization? Do they impact another group? | On Track Slowed Stalled |  |  |  |  | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED

## 2. Process Help
RISK MANAGEMENT PROCESS: OVERVIEW
1. The SCOPE, CONTEXT, and CRITERIA identifies the subject of the risk assessment. For Guidance, See Tab 3.
2. IDENTIFY risks by asking, "What could occur that would have an impact on our objectives?" Risks have three key elements: Event, causes, impacts.
3. Risks ANALYSIS involves ranking the likelihood and consequence using a 1-5 scale. For Guidance, See Tab 4.
4. In order to EVALUATE risks the group reviews the effectiveness and appropriateness of currents controls and determines what action to take, if any. For Guidance, See Tab 5.
5. Risk TREATMENT is the activity (s) you are going to implement to better manage your exposures. Your mitigations will reduce the likelihood and/or consequence of the risk event occurring.
for more information, please see the Risk Management Guideline for the B.C. Public Sector.

## 3. Assessment Context
CONTEXT TEMPLATE
ESTABLISH CONTEXT: The first step in any risk assessment is to set the context. Use this optional template to establish scope, criteria, and deliverable for your organization. Refer to your organizations's Mandate Letter, Service Plan, and other strategic initiatives.
1. State the Business Objectives/Priorities of your organization.
Text text text.
2. State the mission, vision, operating principles and any other value criteria.
Text text text.
3. Identify stakeholders; determine their influence on the organizations's objecitves, methods of consultation and communciation, as appropriate.
Text text text.
4. Set out assumptions and constraints (deadlines, time-frames, environmental factors, or executive directives).
Text text text.

## 4. L&C Matrix
RISK RATING MATRIX (LIKELIHOOD AND CONSEQUENCE)
Likelihood and Consequence Descriptors for Risk Assessments
Likelihood | Rating | Criteria | Probability
Almost certain | 5 | It is expected to happen. Will certainly happen this fiscal year or during the three year period of the Service Plan. | 80% to 100% or once a year or more frequently
Likely | 4 | We expect it to happen. It would be surprising if this did not happen. | 61% to 79% or once every 3 yrs
Possible | 3 | Just as likely to happen as not. We don't expect it to happen, but there is a chance. | 40% to 60% or once every 5 yrs
Unlikely | 2 | Not anticipated. We won't worry about it happening. | 11% to 39% or once every 15 years
Almost certain not to happen | 1 | It would be surprising if this happened. There would have to be a combination of unlikely events for it to happen. | 0 to 10% or once every 25 yrs
Consequence | Rating | Criteria / Examples
Catastrophic | 5 | - Major problem from which there is no recovery. - Significant damage to organization credibility or integrity. - Complete loss of ability to deliver a critical program.
Major | 4 | - Event that requires a major realignment of how service is delivered. - Significant event which has a long recovery period. - Failure to deliver a major political commitment.
Moderate | 3 | - Recovery from the event requires cooperation across departments. - May generate media attention.
Minor | 2 | - Can be dealt with at a department level but requires Executive notification. - Delay in funding or change in funding criteria. - Stakeholder or client would take note.
Insignificant | 1 | - Can be dealt with internally at the business unit level. - No escalation of the issue required. - No media attention. - No or manageable stakeholder or client interest.
Risk Rating Matrix

## 5. Evaluation
RISK EVALUATION
In order to EVALUATE risks, the ADEQUACY OF CURRENT TREATMENTS (Column L) and ACTION (Column M) are determined ADEQUACY OF CURRENT TREATMENTS: Use the drop-down in Column L to identify the risk tolerance of the organization considering the current treatments. Choices include: - Non-existent: there are no current treatments identified in Column G (are not doing anything) - Inadequate: the current treatments (Column G) do not meet the organization's risk tolerance and need attention (are not doing enough) - Adequate: the current treatments (Column G) meet the organization's risk tolerance and no further action is required (are doing enough) - Robust: the current treatments (Column G) exceed the organization's risk tolerance (are doing too much) ACTION: Use the drop-down in Column M to identify the action the organization will take to respond to the risk, if any Choices incude: - Accept: no further action is required - Monitor: Accept and keep an eye on future trends that may impact the currently accepted risk tolerance - Treat: implement ADDITIONAL TREATMENTS to either reduce the likelihood (Column H) or reduce the impact if the risk event occurs (Column I) - Transfer: allocate the risk responsibility to another party through legal contract (e.g. hire another party and transfer the risk to them) - Avoid: do not pursue the objective to avoid the potential consequences identified that are outside of the risk tolerance of the organization TREND: Use the drop-down in Column N to identify the trend of the risk rating since the last reporting period (if applicable). Choices incude: - New Risk: the risk was not included in the last reporting period - Downward: the risk rating (Column J) has decreased since the last reporting period - Static: the risk rating (Column J) has not changed since the last reporting period - Upward: the risk rating (Column J) has increased since the last reporting period

## Sample
--SAMPLE -- XYZ Organization
This risk assessment is connected to/aligns with: |  |  | Enterprise wide operational risk register
Objective: |  |  | Directive by VP of IT Department
Date of the risk assessment: |  |  | <date>
Risk should be reassessed periodically throughout the life of the program or project.
Future date(s) to reassess the risks within the register: |  |  | <date>
Check out the B.C. Enterprise Risk Categories Tool to explore other risks that may affect objectives. | [19 empty] | RISK REPORTING (Optional - Hide/Delete if not in use)
RISK MANAGEMENT PROCESS (For Guidance, See Tab 2) |  | CONTEXT (For Guidance, See Tab 3) | RISK IDENTIFICATION |  |  |  | ANALYSIS Residual risk rating with treatments in place (For Guidance, See Tab 4) |  |  |  | EVALUATION (For Guidance, See Tab 5) |  |  | TREATMENT MANAGEMENT | [5 empty] | TRACKING |  |  |  | RESIDUAL RISK RATING (Risk rating expected / predicted once all mitigations Additional Mitigations are in place.) |  |  |  | CURRENT RISK RATING (Current level of risk in light of mitigations implemented at this report period.) |  |  |  | RISK TOLERANCE RATING (Maximum level of risk executive is willing to accept. This should be provided by executive after having been briefed on the risk, existing and planned mitigations, and associated costs)
RISK # | CATEGORY | BUSINESS OBJECTIVE/ PRIORITY | RISK EVENT | RISK CAUSE | IMPACT | CURRENT TREATMENTS | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | ADEQUACY OF CURRENT TREATMENTS | ACTION | TREND | ADDITIONAL PLANNED TREATMENT | DELIVERABLES | TASK OWNER | DUE DATE | DEPENDENCIES/ INTER-RELATIONSHIPS | STATUS | PROGRESS % | COMMENTS/ ISSUES | FURTHER ACTION | COMPLETION DATE | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP
Add identifiers to better organize and track risks. | Which category does this Risk Event fall under? | What business objective/priority does this Risk Event affect (e.g., Mandate letter, strategic directive, etc.)? | What events could impact the achievement of objectives (can be positive or negative)? | What Risk Cause (trigger, circumstance, uncertainty) could increase the Likelihood of the Risk Event occurring? There are usually multiple Risk Causes leading to a Risk Event. | How would the Risk Event impact the achievement of the objective/priority? | What Treatments are currently in place to manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | How likely? | How severe? | (LxC) | Rating with current treatments in place | Non-existent Inadequate Adequate Robust | Will you do more to manage the risk (treat) or choose to accept and monitor? | If applicable, has this risk rating changed over time? Has column J increased (upward trend), decreased (downward trend) or not changed (static) | What Treatments are needed to further manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | Future Treatments will come in what form (e.g., a project plan, a briefing note, report, funding request, other)? | Who will take the lead on this mitigation? | When should the deliverable be ready? (Optional) | Do the Risk Event or Treatments depend on another team or organization? Do they impact another group? | On Track Slowed Stalled |  |  |  |  | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place
OFP 1 | Operational - Financial Processes | Timely service delivery to clients. | Invoice delivery to clients is slow and inaccurate. | - Legacy system is incompatible with data input requirements. - Data entry practices inconsistent - Manual data checks | - Unmet client service quality performance - Increased A/R - Increased risk of loss - Increased cost of recovery | - Manual data checks - Training manual | 3 | 4 | 12 | HIGH | Inadequate | Treat | Downward | Long term: - System replacement Short term: - Update training manual - Commit more staff time. | - System replacement strategy - Revised training manual and web counterpart - Staffing solution for short term | - Systems replacement: Tom - Training manual: Sarah - Staff review: Tom | - System replacement strategy: End of fiscal - Training manual: February 14th - Staffing review and recommendation: February 7th | System shared with IT Department. |  | 25% - Initial planning complete. Implementation expected once additional staff sourced. | Further progress is dependant upon staffing approval |  |  | 2 | 4 | 8 | MEDIUM | 3 | 4 | 12 | HIGH | 2 | 4 | 8 | MEDIUM
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED