## HELP GUIDE
Project Status Reporting Template Help Guide
Purpose:
Status reports are a communication tool between the Project Manager and Project Sponsor, Steering Committee, IMB Managers as well as within the Project Team. They document the status of the project at a point in time, within a regular interval, e.g. bi-weekly or monthly. The status is evaluated based on scope, quality, time, budget, and FTE resources. Notes are added to clarify the status, describe issues and remediation steps, and comment on milestones, deliverables and dependencies.
Status reports for IMB internal projects are submitted to the CSNR IMB SP/PMO mailbox. This information will be used for branch-wide reporting and provides a summary of all internal work IMB staff are undertaking. The template will be used for all projects IMB management requests reporting on.
The following detail provides guidance on the requirements for each section of the report.
Project Tombstone Information
This information seldom changes during the project and is primarily collected once when the first report is created. The exception is the reporting period that is updated to reflect the time frame of the status report.
Project Name and Project Number – unique identifiers for this activity
Project Description – Brief description of the project (which can be taked from Information Systems Plan (ISP), Project Charter, etc). Note: By default this section is hidden. If a project description is required on the status report unhide rows 6 and 7 and enter your information.
Reporting Period – the start and end dates of the time period the activities occurred
Project Sponsor – identification of the sponsor and business area
Project lead – the person leading the work and has the role of project manager (e.g. name of BPM)
Report Preparer – the person completing the report and date completed (may or may not be the Project lead)
Hyperlink to Project Repository – the location where project documentation will be stored (project charter, master project plan, status reports, meeting minutes, etc). Insert a hyperlink.
Dashboard Summary
Graphic representation of the overall project progress. Visually using Green, Yellow and Red quickly shows where the project is tracking well or has serious issues. To ensure understanding for all reviewers put the initial of the appropriate color in the box.
For consistency, reference the table below to determine whether the component is Red, Yellow, or Green.
| Red (serious concerns) | Yellow (in control) | Green
Scope | Serious scope concerns | Minor scope concerns | No concerns
Quality | Final product will not meet requirements or expectations | Concerned that quality will not be sufficient | No concerns
Time | Serious schedule delay | Minor Schedule delay | On Schedule
Budget | Over budget – extra funding needed | Concerned that there may not be enough budget | On Budget
FTE Resources | Serious resource challenges | Concern that resources not available | Resources available
Conditional formating has been created for these dashboard summaries. When R, Y or G is entered the cell will colour accordingly.
Ensure that any status that reflects “Yellow” or “Red” have sufficient detail documented in the Comment Field to the right of the Dashboard column so reviewers can understand the issue or crisis.
Financial Summary
To be completed if the project is allocated Operational or Capital funding.
Key Milestones/ Deliverables
Identification of specific milestones or deliverables being worked on during the reporting period. Business Architecture, Initiation, Analysis, Design, Build, and Implementation are all SDLC phases. If the project does not follow the SDLC then Initiation, Development, Implementation, Close-out might be more appropriate phases to use. Others phases and milestones can be added.
This section includes rough scheduling (target and revised start date, and target end date) plus an estimate of completed work (% complete). Completed items are shown as 100% complete with an end date during the one reporting period and can then be removed or hidden.
Comments column can include issues, accomplishments, planned activities, etc. that are related to each milestone or deliverable. If desired, additional rows can be included beneath a specific milestone/deliverable to document additional items.
High Level Project Dependencies
Complete at the beginning of the project to identify dependencies for the project. Update the dependencies as required through the life of the project.

## Status Report
STATUS REPORT
Project Name: | [6 empty] | Project #:
Reporting Period: |  |  | Start Date: |  |  | End Date:
Project Sponsor: |  |  |  |  | Business Portfolio Manager:
This Report Prepared By: | [6 empty] | Hyperlink to Project Repository
Project Description
Project Dashboard (overall status)
Scope |  | <Enter G, Y or R> | <additional comments to clarify the ranking – Why Red or Yellow – include description of issues and remediation comments>
Quality |  | <Enter G, Y or R>
Time |  | <Enter G, Y or R>
Budget |  | <Enter G, Y or R>
FTE Resources |  | <Enter G, Y or R>
Overall Fiscal Project Funding (if applicable)
Capital $ Allocated |  |  | 0 |  | Operating $ Allocated |  | 0
Capital $ Actual: |  |  | 0 |  | Operating $ Actual: |  | 0
Capital $ Forecast |  |  | 0 |  | Operating $ Forecast |  | 0
Key Milestones / Deliverable (for this reporting period)
Major Milestones and Deliverables: |  |  | Target Start Date | Revised Date | Target End Date | % Complete | Comments
1 | Business Architecture
2 | Initiation
3
4 | Analysis
5
6 | Design
7
8 | Build
Project High Level Dependencies:
Other applications: |  |  |  |  | Other agencies:
Other initiatives: |  |  |  |  | Business cycles:
Legislation: |  |  |  |  | Business policy:
Other:

## Status Details
STATUS REPORT - Details
Project Detail:
Tasks Completed in this Reporting Period
Tasks planned for Next Reporting Period
Action Items
#