## Project Planning Tool
Project Planning Tool
Project Name/Number: | [5 empty] | Project Description:
Coordinating Registered Professional (CRP): | [5 empty] | Road Activity POR (RAPOR):
Crossing CRP: | [5 empty] | Crossing POR (RAPOR):
Considered
Phase |  | YES | NO | N/A | Reference |  | Comments | Initials | Date
Planning | Pre-Planning |  |  |  |  | Determine need for project: Inspection Reports or Capital Project/Service Plan
Ensure there is an Approved FSP
Create Project folder
Planning Funding in Place - Approval to Proceed
Field Recce / ID crossing location (Consider involving Eng Branch at this time)
Run status report
| Consultation |  |  |  |  | Lands Conflicts
FN Impact Assessment
First Nations Engagement (Consultation or Notification)
Archaeological Assessment
Communities
Stakeholders (trappers,
General Public (website notification or Drive BC)
| Develop Work Plan |  |  |  |  | Identify Rip Rap needs and location (Consider ML/ARD)
Identify Spoil Sites and location
Identify Ballast/Capping/Gravel needs and location (Consider ML/ARD)
Terrain Stability Assessment
Karst Assessment
Fisheries/Biological Assessment (Fish or Non-Fish Crossings)
Migratory Birds Assessment
Site Survey (Contract or in house)
General Arrangement and Structural Designs
Engineering Branch Review of General Arrangement Design
Obtain Site/Structure ID and add it to CBR (Eng Branch)
Consider comments from Peer Review
For BCTS Material Supply: Review/collect structural designs
For BCTS Material Supply: In-Plant inspections/Mill Certificates Report
Obtain license to cut or section 51 authorization to deal with ROW timber
Consider Bypass requirements/closure
Consider Disposal or Storage of obsolete structure
Consider signage needs
Consider Project Monitor
Consider adequate staging area size
Written Cost Estimate
Consider Species at Risk
Consider Noxious Weeds
Field Layout/Ribbon
Consider access issues
| Safety Considerations for Pre-work |  |  |  |  | Danger Tree Assessment
Fall Arrest System Requirements
Rainfall Shutdown Criteria (from TSA)
Traffic Control Requirements
Emergency Response Plan
Communication Plan
| Environmental |  |  |  |  | Environmental Management Plan (EMP). Include Spill/Incident Response Plan
Fish Timing Windows
Fish Salvage Requirements/Permitting
DFO Review/Authorization (Consider DFO Codes of Practice)
Water Sustainability Act Approval
Community Watershed Notification requirements
Sediment Control Plan and Equipment Needs
Environmental Monitoring needs
TSL Transfer | [5 empty] | If transferring to TSL Holder CRP: Ensure handoff form is completed and all relevant documentation has been provided to the TSL Holder's CRP. Checklist can stop here if transferring to another CRP.
Solicitation and Award | [5 empty] | Project Funding Approved/in place
Identify the Contract Manager
Ensure contract documents reflect all relevant assessments, construction timing, and budgets
POR to provide input on Schedule C details for materials
Post Tender | [5 empty] | For Contractor Material Supply: Review/collect structural design by contractor
For Contractor Material Supply: In-Plant inspections/Mill Certificates Report
Review contractor references and mandatories
Ensure a signed contract for works is on file
Encumbrance Form
Construction | [5 empty] | Ensure Pre Work Meeting is held to discuss details of works, assessments, timing, etc.
Ensure there is an appropriate level of construction details (launch plans, stream crossings, etc.)
Ensure there is an appropriate level of construction Inspections/Visits
Ensure compliance with applicable assessments, reports, standards, and design
Ensure changes of condition meeting initial intent of planned work
Completion | [5 empty] | Final Field Inspection
Letter of Completion to FN
Grout Testing Results
Professional of Record: Crossing Assurance Statement and As Built Record Drawing, FS138
Environmental Monitor: Construction Report
Send finalized works to Eng Branch for updates in CBR
Final Construction Monitor Report: Summary of contracted works, identification of issues, record of project
CRP to complete FS1414 (Structure) or FS1365 (Deactivation) or FS1366 (Road Construction) and compile final package
CRP Final Package Contents |  | Yes | No | N/A |  | Comments/Location Filed |  | Initials | Date
Fisheries/Biological Assessment
Archeology Assessment
Terrain Stability Assessment
Migratory Birds Assessment
Karst Assessment
Environmental Management Plan (SDMP)
Structural Design
Mill Certificates/In-plant inspection Report
Environmental Monitors Final Report
As-Built Record Drawings
Grout Testing Results
FS138 - Statement of Construction Conformance - POR
Final Construction Monitor Report
Assurance Statement CRP - FS1414 or 1365 or 1366